## Planning
Planning | Start | Deadline | Aantekening | Werkdagen | Active task | Finished
Project plan met initiele planning | 2017-09-04 | 2017-10-06 |  | 25 | 0 | 1 | 2018-03-06
Samenvatten gerelateerde projecten en onderzoeken | 2017-10-04 | 2017-10-20 |  | 13 | 0 | 1
Plan van aanpak met opzet voor report | 2017-10-09 | 2017-11-03 |  | 20 | 0 | 1
Inlezen in papers en project, omzetten naar current knowledge | 2017-10-20 | 2017-11-19 |  | 21 | 0 | 1
Plan van aanpak overleggen met begeleiders | 2017-11-20 | 2017-11-26 |  | 5 | 0 | 1
Programma van eisen thesis (abstract model van onderzoek) | 2017-11-26 | 2017-12-10 |  | 10 | 0 | 1
Manoeuvring capabilities input definieren | 2017-12-10 | 2017-12-24 |  | 10 | 1 | 0.9
Map information at the bridge | 2017-12-25 | 2018-01-14 |  | 15 | 1 | 0.7
Communication in theory | 2017-12-18 | 2018-01-21 |  | 25 | 1 | 0.6
Probability index | 2018-01-22 | 2018-02-18 |  | 20 | 1 | 0.5
Safe motion parameters | 2018-02-19 | 2018-03-04 |  | 10 | 1 | 0
Filter situation | 2018-03-05 | 2018-03-18 |  | 10 | 1 | 0
Mental model | 2018-03-19 | 2018-04-08 |  | 15 | 0 | 0
Possible decisions | 2018-04-09 | 2018-04-18 |  | 8 | 0 | 0
Build cases | 2018-04-19 | 2018-04-30 |  | 8 | 0 | 0
Test with seafarers | 2018-05-01 | 2018-05-06 |  | 4 | 0 | 0
Iterate tool and model | 2018-05-07 | 2018-05-20 |  | 10 | 0 | 0
Finalize report | 2018-05-21 | 2018-06-02 |  | 10 | 0 | 0
Write article | 2018-06-04 | 2018-06-24 |  | 15 | 0 | 0
Make and practice presentation | 2018-06-24 | 2018-07-06 |  | 10 | 0 | 0
Formulas:
Werkdagen = NETWORKDAYS([Start],[Deadline])

## Mensen in de loop
Toine Cleophas | Begeleider Damen
Robert Hekkenberg | Begeleider Maritiem
Mark Neerincx | Begeleider Computer science
Piet Faasse | Director Electrical & Automation
Martijn de Munnik | Engineer Service, Maintenance Analysis & Technical advice. Veel verstand van programeren
Siebe Rooijakkers | R&D geeft veel input
Hans van den Broek | STC - Lector maritieme human factors
Monique van der Drift | STC - Opleidings coordinator en docent
Marcel Vermeulen | RH Marine - Sales Integrated bridge systems, helpt met ECDIS
Siebe Rooijakkers | Development, autonoom bootje TU Delft
Egbert Ypma | Marin - researcher
Johan de Jong | Marin - international cooperation

## Quotes
Auteur | Quote | Quote english | Bron
Epictetus | Het is onmogelijk om te leren wat je denkt reeds te weten | It is impossible for a man to learn what he thinks he already knows | Scheurkalender NewScientist 2017
Marvin Minsky |  | We rarely recognize how wonderful it is that a person can traverse an entire lifetime without making a single really serious mistake — like putting a fork in one's eye or using a window instead of a door. | Scheurkalender NewScientist 2017