## Planning
Planning | Start | Deadline | Aantekening | Werkdagen | Active task | Finished
Project plan met initiele planning | 2017-09-04 | 2017-10-06 |  | 25 | 0 | 1 | 2018-09-26
Samenvatten gerelateerde projecten en onderzoeken | 2017-10-04 | 2017-10-20 |  | 13 | 0 | 1
Plan van aanpak met opzet voor report | 2017-10-09 | 2017-11-03 |  | 20 | 0 | 1
Inlezen in papers en project, omzetten naar current knowledge | 2017-10-20 | 2017-11-19 |  | 21 | 0 | 1
Plan van aanpak overleggen met begeleiders | 2017-11-20 | 2017-11-26 |  | 5 | 0 | 1
Programma van eisen thesis (abstract model van onderzoek) | 2017-11-26 | 2017-12-10 |  | 10 | 0 | 1
Manoeuvring capabilities input definieren | 2017-12-10 | 2017-12-24 |  | 10 | 1 | 0.9
Map information at the bridge | 2017-12-25 | 2018-01-14 |  | 15 | 1 | 0.7
Communication in theory | 2017-12-18 | 2018-01-21 |  | 25 | 1 | 0.6
Probability index | 2018-01-22 | 2018-02-18 |  | 20 | 1 | 0.5
Safe motion parameters | 2018-02-19 | 2018-03-04 |  | 10 | 1 | 0
Filter situation | 2018-03-05 | 2018-03-18 |  | 10 | 1 | 0
Mental model | 2018-03-19 | 2018-04-08 |  | 15 | 1 | 0
Possible decisions | 2018-04-09 | 2018-04-18 |  | 8 | 1 | 0
Build cases | 2018-04-19 | 2018-04-30 |  | 8 | 1 | 0
Test with seafarers | 2018-05-01 | 2018-05-06 |  | 4 | 1 | 0
Iterate tool and model | 2018-05-07 | 2018-05-20 |  | 10 | 1 | 0
Finalize report | 2018-05-21 | 2018-06-02 |  | 10 | 1 | 0
Write article | 2018-06-04 | 2018-06-24 |  | 15 | 1 | 0
Make and practice presentation | 2018-06-24 | 2018-07-06 |  | 10 | 1 | 0
Formulas:
Werkdagen = NETWORKDAYS([Start],[Deadline])

## Mensen in de loop
Toine Cleophas | Begeleider Damen
Robert Hekkenberg | Begeleider Maritiem
Mark Neerincx | Begeleider Computer science
Piet Faasse | Director Electrical & Automation
Martijn de Munnik | Engineer Service, Maintenance Analysis & Technical advice. Veel verstand van programeren
Siebe Rooijakkers | R&D geeft veel input
Hans van den Broek | STC - Lector maritieme human factors
Monique van der Drift | STC - Opleidings coordinator en docent
Marcel Vermeulen | RH Marine - Sales Integrated bridge systems, helpt met ECDIS
Siebe Rooijakkers | Development, autonoom bootje TU Delft
Egbert Ypma | Marin - researcher
Johan de Jong | Marin - international cooperation
Martijn Drenth | Loodswezen - Pilot en Board
Gijs ten Stege | Maritime Support

## Quotes
Report | Auteur | Quote | Quote english | Bron
Part I | Epictetus | Het is onmogelijk om te leren wat je denkt reeds te weten | It is impossible for a man to learn what he thinks he already knows | Scheurkalender NewScientist 2017
Part II | Marvin Minsky |  | We rarely recognize how wonderful it is that a person can traverse an entire lifetime without making a single really serious mistake. Like putting a fork in one's eye or using a window instead of a door. | Scheurkalender NewScientist 2017
Voorwoord | Hekkenberg | Ga ervan uit dat de lezer dom, lui en vergeetachtig is | Assume the reader is stupid, lazy and oblivious | Meeting 11-04-2018
Voorwoord | Hekkenberg | Een slecht ontwerp dat goed wordt verkocht, faalt uiteindelijk. Een goed ontwerp dat slecht wordt verkocht, faalt onmiddellijk | A poor design well sold fails eventually, a good design poorly sold fails immediately | Continuesly in 2018
| Paula Scher |  | It's through mistakes that you actually grow. You have to get bad in order to get good. | Psychology today, 2009
Part III | Marcus Rall |  | Meant is not said, said is not heard, heard is not understood, understood is not done | \cite{Rall2005}
Part IV | Galileo Galilei |  | All truths are easy to understand once they are discovered. The point is to discover them. | Dialogo sopra i due massimi sistemi del mondo (1632), Day two:
| Antoine de Saint-Exupery | Créer le navire ce n’est point tisser les toiles, forger les clous, lire les astres, mais bien donner le goût de la mer qui est un, et à la lumière duquel il n’est plus rien qui soit contradictoire mais communauté dans l’amour. | Building a boat isn’t about weaving canvas, forging nails, or reading the sky. It’s about giving a shared taste for the sea, by the light of which you will see nothing contradictory but rather a community of love. | Citadelle, 1948
| Carl Jung |  | Every individual is an exception to the rule. Therefore, one can never give a description of a type, no matter how complete, which applies to more than one individual despite the fact that thousands might, in a certain sense, be strikingly described thereby. Conformity is one side of a man, uniqueness is the other. | Psychologische Typen, 1925
Part V | Yuval Noah Harrari |  | Studying history will not tell us what to choose, but at least gives us more options to choose from. | Homo Deus